## Cover Sheet
New Codington Festival Online Project/FERS (Release 2)
Test Cycle Control Sheet Template - Unit Test (Sample Solution)
Version: <1.3>
This document is used to plan test script execution for the New Codington Festival Online project. It has been used to define each unit test cycle and capture the test scripts which will be executed within each unit test cycle. This sheet will also be used to track testing execution progress. Since the unit tests are run in isolation, order of the test script execution is not as important as in the other test stages where the Java class modules are integrated together (e.g. Assembly, Product, Performance, UAT, etc.). The scripts and cycles are listed by function of FERS to ensure all scenarios are covered. Also since unit tests should cover business cases, and not focus on implementation details, other developers should be able to read these unit tests to understand the business functionality of the code being tested. FACULTY PLEASE NOTE: All highlighed cells makes up the sample solution to be provided by the participants. The script defintions will differ because the participants will provide a subset of the full number of scenarios.

## TCCS
Enter the start date in cell G7 to populate the plan.
[5 empty] | 2015-05-24 | [6 empty] | 2015-05-31 | [6 empty] | 2015-06-07 | [6 empty] | 2015-06-14 | [6 empty] | 2015-06-21 | [6 empty] | 2015-06-28 | [6 empty] | 2015-07-05 | [6 empty] | 2015-07-12 | [6 empty] | 2015-07-19
Cycle Profile Details |  |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Execution |  |  |  | Pass 1 |  | Pass 2 |  | Pass 3
Test Cycle ID | Scenario ID | Test Cycle Description | Test Script ID | Test Script | [63 empty] | Tester | Pass 1 | Pass 2 | Pass 3 | Started | Ended | Started | Ended | Started | Ended | Tester | time axis 2015-05-24 to 2015-07-25
 | time axis 2015-05-24 to 2015-07-25
1 |  | VISITORCONTROLLER - newVisitor() | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
1.1 |  | Register New Visitor (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.001.01 | Attempt to create a new visitor (all parameters are populated in Request Object) | FERS.UT.AP491.S.001 | FERS_UT_AP491_S_001.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.001.02 | Attempt to create a new visitor (all NOT NULL parameters are populated, some NULL parameters are NOT populated) | FERS.UT.AP491.S.001 | FERS_UT_AP491_S_001.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
1.2 |  | Register New Visitor (negative) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.002.01 | Attempt to create a new visitor (visitor already exists in system) | FERS.UT.AP491.S.001 | FERS_UT_AP491_S_001.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
1.3 |  | Register New Visitor (exception) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.003.01 | Attempt to create a new visitor (missing Request object) | FERS.UT.AP491.S.001 | FERS_UT_AP491_S_001.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.003.02 | Attempt to create a new visitor (missing Reponse object) | FERS.UT.AP491.S.001 | FERS_UT_AP491_S_001.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.003.03 | Attempt to create a new visitor (missing objects) | FERS.UT.AP491.S.001 | FERS_UT_AP491_S_001.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
2 |  | VISITORCONTROLLER - searchVisitor() | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
2.1 |  | Visitor Login (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.004.01 | Attempt to find visitor using login credentials (valid username and password) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
2.2 |  | Visitor Login (negative) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.005.01 | Attempt to find visitor using login credentials (invalid username) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.005.02 | Attempt to find visitor using login credentials (valid username, invalid password) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.005.03 | Attempt to find visitor using login credentials (empty Values for username and password) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
2.3 |  | Visitor Login (exception) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.006.01 | Attempt to find visitor using login credentials (missing object) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.006.02 | Attempt to find visitor using login credentials (missing object) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.006.03 | Attempt to find visitor using login credentials (missing objects) | FERS.UT.AP491.S.002 | FERS_UT_AP491_S_002.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
3 |  | VISITORCONTROLLER - updateVisitor() | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
3.1 |  | Update Visitor Information (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.007.01 | Attempt to update visitor information (all parameters are populated) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.007.02 | Attempt to update visitor information (all NOT NULL parameters are populated, some NULL parameters are NOT populated) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
3.2 |  | Update Visitor Information (negative) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.008.01 | Attempt to update visitor information (visitor DOES NOT exist in system) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
3.3 |  | Update Visitor Information (exception) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.009.01 | Attempt to update visitor information (missing Visitor attribute) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.009.02 | Attempt to update visitor information (missing request object) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.009.03 | Attempt to update visitor information (missing response object) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.009.04 | Attempt to update visitor information (missing objects) | FERS.UT.AP491.S.003 | FERS_UT_AP491_S_003.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
4 |  | VISITORCONTROLLER - registerVisitor() | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
4.1 |  | Register for Event (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.010.01 | Attempt to register visitor for an event (valid visitor and event, not registered for event) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
4.2 |  | Register for Event (negative) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.011.01 | Attempt to register visitor for an event (valid visitor and event, registered for event) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
4.3 |  | Register for Event (exception) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.012.01 | Attempt to register visitor for an event (missing Visitor attribute) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.012.02 | Attempt to register visitor for an event (missing eventID parameter) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.012.03 | Attempt to register visitor for an event (missing request object) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.012.04 | Attempt to register visitor for an event (missing response object) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.012.05 | Attempt to register visitor for an event (missing request and response object) | FERS.UT.AP491.S.004 | FERS_UT_AP491_S_004.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
5 |  | VISITORCONTROLLER - unregisterVisitor() | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
5.1 |  | Unregister from Event (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.013.01 | Attempt to unregister visitor from an event (valid visitor and event, registered for event) | FERS.UT.AP491.S.005 | FERS_UT_AP491_S_005.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
5.2 |  | Unregister from Event (negative) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.014.01 | Attempt to unregister visitor from an event (valid visitor and event, not registered for event) | FERS.UT.AP491.S.005 | FERS_UT_AP491_S_005.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
5.3 |  | Unregister from Event (exception) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.015.01 | Attempt to unregister visitor from an event (missing request object) | FERS.UT.AP491.S.005 | FERS_UT_AP491_S_005.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.015.02 | Attempt to unregister visitor from an event (missing response object) | FERS.UT.AP491.S.005 | FERS_UT_AP491_S_005.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.015.03 | Attempt to unregister visitor from an event (missing objects) | FERS.UT.AP491.S.005 | FERS_UT_AP491_S_005.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
6 |  | EVENTCONTROLLER - getAvailableEvents() | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
6.1 |  | Retrieve Available Events (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.016.01 | No available events for the visitor(request and response object passed) | FERS.UT.AP491.S.006 | FERS_UT_AP491_S_006.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.016.02 | One available events for the visitor(request and response object passed) | FERS.UT.AP491.S.006 | FERS_UT_AP491_S_006.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.016.03 | More than one available events for the visitor(request and response object passed) | FERS.UT.AP491.S.006 | FERS_UT_AP491_S_006.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
6.2 |  | Retrieve Available Events (exception) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.017.01 | See all available events for the visitor(null request object) | FERS.UT.AP491.S.006 | FERS_UT_AP491_S_006.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.017.02 | See all available events for the visitor(null response object) | FERS.UT.AP491.S.006 | FERS_UT_AP491_S_006.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.017.03 | See all available events for the visitor(both objects are null ) | FERS.UT.AP491.S.006 | FERS_UT_AP491_S_006.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
7 |  | EVENTDAO - showAllEvents() | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
7.1 |  | Show All Events (positive) | [65 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.018.01 | Successfully retrieve no events | FERS.UT.AP491.S.007 | FERS_UT_AP491_S_007.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.018.02 | Successfully retrieve one event | FERS.UT.AP491.S.007 | FERS_UT_AP491_S_007.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.018.03 | Successfully retrieve more than one event | FERS.UT.AP491.S.007 | FERS_UT_AP491_S_007.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
7.2 |  | Show All Events (Exception) | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.019.01 | Attempt to connection to database (invalid JDBC Driver) | FERS.UT.AP491.S.007.a | FERS_UT_AP491_S_007a.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.019.02 | Attempt to connection to database (invalid URL) | FERS.UT.AP491.S.007.a | FERS_UT_AP491_S_007a.java | [63 empty] | Mahesh Jayashankar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
8 |  | EVENTDAO - updateEventNominations() | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
8.1 |  | Update Event Nominations (Positive) | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.020.01 | Attempt to update (decrease) number of available tickets (event to update is valid and there is more than zero tickets available) | FERS.UT.AP491.S.008 | FERS_UT_AP491_S_008.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.020.02 | Attempt to update (decrease) number of available tickets (event to update is valid but there are zero tickets) | FERS.UT.AP491.S.008 | FERS_UT_AP491_S_008.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
8.2 |  | Update Event Nominations (Exception) | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.021.01 | Attempt to update (decrease) number of available tickets (event to update is not in system) | FERS.UT.AP491.S.008 | FERS_UT_AP491_S_008.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.021.02 | Attempt to connection to database (invalid JDBC Driver) | FERS.UT.AP491.S.008.a | FERS_UT_AP491_S_008a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.021.03 | Attempt to connection to database (invalid URL) | FERS.UT.AP491.S.008.a | FERS_UT_AP491_S_008a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
9 |  | EVENTDAO - checkEventsofVisitor() | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
9.1 |  | Check Events of Visitor (positive) | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.022.01 | Attempt to check if the visitor already registered for the event (visitor has registered for the event) | FERS.UT.AP491.S.009 | FERS_UT_AP491_S_009.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
9.2 |  | Check Events of Visitor (negative) | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.023.01 | Attempt to check if the visitor already registered for the event (visitor has NOT registered for the event) | FERS.UT.AP491.S.009 | FERS_UT_AP491_S_009.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.023.02 | Attempt to check if the visitor already registered for the event (eventID is invalid) | FERS.UT.AP491.S.009 | FERS_UT_AP491_S_009.java | [64 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
9.3 |  | Check Events of Visitor (Exception) | [66 empty] | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.024.01 | Attempt to check if the visitor already registered for the event (Visitor is NULL) | FERS.UT.AP491.S.009a | FERS_UT_AP491_S_009a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.024.02 | Exception is thrown | FERS.UT.AP491.S.009a | FERS_UT_AP491_S_009a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
10 |  | EVENTDAO - updateEventDeletions() | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
10.1 |  | Update Event Deletions (Positive) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.025.01 | Attempt to update (increase) number of available tickets (event to update is valid) | FERS.UT.AP491.S.010 | FERS_UT_AP491_S_010.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
10.2 |  | Update Event Deletions (Negative) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.026.01 | Attempt to update (increase) number of available tickets (event to update is invalid) | FERS.UT.AP491.S.010 | FERS_UT_AP491_S_010.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
10.3 |  | Update Event Deletions (Exception) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.027.01 | Attempt to update (increase) number of available tickets (statement object not available) | FERS.UT.AP491.S.010a | FERS_UT_AP491_S_010a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.027.02 | Attempt to update (increase) number of available tickets (connection object not available) | FERS.UT.AP491.S.010a | FERS_UT_AP491_S_010a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
11 |  | VISITORDAO - insertData() | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
11.1 |  | Insert New Visitor information (Positive) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.028.01 | Insert New Visitor information into Database (username not already used in system) | FERS.UT.AP491.S.011 | FERS_UT_AP491_S_011.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
11.2 |  | Insert New Visitor information (Negative) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.029.01 | Insert New Visitor information into Database (username already in use in system) | FERS.UT.AP491.S.011 | FERS_UT_AP491_S_011.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
11.3 |  | Insert New Visitor information (Exception) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.030.01 | Insert New Visitor information into Database (invalid visitor Object) | FERS.UT.AP491.S.011.a | FERS_UT_AP491_S_011a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.030.02 | Attempt to insert new visitor information(JDBC Driver not found) | FERS.UT.AP491.S.011.a | FERS_UT_AP491_S_011a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.030.03 | Attempt to insert new visitor information(Unable to get a connection) | FERS.UT.AP491.S.011.a | FERS_UT_AP491_S_011a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
12 |  | VISITORDAO - searchUser() | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
12.1 |  | Search for User (Validate login credentials) - Positive | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.031.01 | Attempt to validate login credentials (username and password combination is valid) | FERS.UT.AP491.S.012 | FERS_UT_AP491_S_012.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
12.2 |  | Search for User (Validate login credentials) - Negative | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.032.01 | Attempt to validate login credentials (username and password combination is invalid) | FERS.UT.AP491.S.012 | FERS_UT_AP491_S_012.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.032.02 | Attempt to validate login credentials (username and password are not passed) | FERS.UT.AP491.S.012 | FERS_UT_AP491_S_012.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
12.3 |  | Search for User (Validate login credentials) - Exception | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.033.01 | Attempt to validate login credentials (statement object not available) | FERS.UT.AP491.S.012.a | FERS_UT_AP491_S_012a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.033.02 | Attempt to validate login credentials (connection object not available) | FERS.UT.AP491.S.012.a | FERS_UT_AP491_S_012a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
13 |  | VISITORDAO - registerVisitortoEvent() | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
13.1 |  | Register Visitor to Event (Positive) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.034.01 | Attempt to register visitor for the event (valid visitor object and event ID) | FERS.UT.AP491.S.013 | FERS_UT_AP491_S_013.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
13.2 |  | Register Visitor to Event (Negative) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.035.01 | Attempt to register visitor for the event (invalid eventID) | FERS.UT.AP491.S.013 | FERS_UT_AP491_S_013.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
13.3 |  | Register Visitor to Event (Exception) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.036.01 | Attempt to register visitor for the event (NO visitor object passed) | FERS.UT.AP491.S.013.a | FERS_UT_AP491_S_013a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.036.02 | Attempt to register visitor for the event (statement object not available) | FERS.UT.AP491.S.013.a | FERS_UT_AP491_S_013a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.036.03 | Attempt to register visitor for the event (connection object not available) | FERS.UT.AP491.S.013.a | FERS_UT_AP491_S_013a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
14 |  | VISITORDAO - registeredEvents() | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
14.1 |  | Displayed Registered Events (Positive) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.037.01 | Attempt to display all events the Visitor is registered for (Valid Visitor - registered for no events) | FERS.UT.AP491.S.014 | FERS_UT_AP491_S_014.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.037.02 | Attempt to display all events the Visitor is registered for (Valid Visitor - registered for one event) | FERS.UT.AP491.S.014 | FERS_UT_AP491_S_014.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.037.03 | Attempt to display all events the Visitor is registered for (Valid Visitor - registered for more than one event) | FERS.UT.AP491.S.014 | FERS_UT_AP491_S_014.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
14.2 |  | Displayed Registered Events (Exception) | [65 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.038.01 | Attempt to display all events the Visitor is registered for (Invalid Visitor object) | FERS.UT.AP491.S.014.a | FERS_UT_AP491_S_014a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.038.02 | Attempt to display all events the Visitor is registered for (statement object not found) | FERS.UT.AP491.S.014.a | FERS_UT_AP491_S_014a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.038.03 | Attempt to display all events the Visitor is registered for (connection object not found) | FERS.UT.AP491.S.014.a | FERS_UT_AP491_S_014a.java | [63 empty] | Uday Chandra Kumar | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
15 |  | VISITORDAO - updateVisitor() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
15.1 |  | Update Visitor Information (Postive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.039.01 | Attempt to update visitor information (Valid visitor) | FERS.UT.AP491.S.015 | FERS_UT_AP491_S_015.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
15.2 |  | Update Visitor Information (Negative) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.040.01 | Attempt to update visitor information (invalid visitor ID ) | FERS.UT.AP491.S.015 | FERS_UT_AP491_S_015.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
15.3 |  | Update Visitor Information (exception) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.041.01 | Attempt to display all events the Visitor is registered for (statement object not found) | FERS.UT.AP491.S.015.a | FERS_UT_AP491_S_015a.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.041.02 | Attempt to display all events the Visitor is registered for (connection object not found) | FERS.UT.AP491.S.015.a | FERS_UT_AP491_S_015a.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
16 |  | VISITORDAO - unregisterEvent() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
16.1 |  | Unregister Visitor from Event (Positive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.042.01 | Attempt to unregister visitor from an event (valid visitor object and event ID) | FERS.UT.AP491.S.016 | FERS_UT_AP491_S_016.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
16.2 |  | Unregister Visitor from Event (Negative) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.043.01 | Attempt to unregister visitor from an event (invalid eventID - visitor not registered to an event with that ID) | FERS.UT.AP491.S.016 | FERS_UT_AP491_S_016.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
16.3 |  | Unregister Visitor from Event (Exception) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.044.01 | Attempt to unregister visitor from an event (NO visitor object passed) | FERS.UT.AP491.S.016.a | FERS_UT_AP491_S_016a.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.044.02 | Attempt to unregister visitor from an event (statement object not available) | FERS.UT.AP491.S.016.a | FERS_UT_AP491_S_016a.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.044.03 | Attempt to unregister visitor from an event (connection object not available) | FERS.UT.AP491.S.016.a | FERS_UT_AP491_S_016a.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
17 |  | EVENTSERVICEIMPL - getAllEvents() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
17.1 |  | Get all available events (Positive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.045.01 | Attempt to retrieve information on all upcoming events (Events found) | FERS.UT.AP491.S.017 | FERS_UT_AP491_S_017.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
17.2 |  | Get all available events (Negative) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.046.01 | Attempt to retrieve information on all upcoming events (No Events found) | FERS.UT.AP491.S.017 | FERS_UT_AP491_S_017.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
18 |  | EVENTSERVICEIMPL - checkEventsofVisitor() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
18.1 |  | Check events registered to Visitor (Positive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.047.01 | Attempt to check if Visitor Registered for the event (Check performed - already registered) | FERS.UT.AP491.S.018 | FERS_UT_AP491_S_018.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
18.2 |  | Check events registered to Visitor (Negative) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.048.01 | Attempt to check if Visitor Registered for the event (Check performed - not already registered) | FERS.UT.AP491.S.018 | FERS_UT_AP491_S_018.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.048.02 | Attempt to check if Visitor Registered for the event (Check performed - Visitor is not valid - Invalid ID) | FERS.UT.AP491.S.018 | FERS_UT_AP491_S_018.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
18.3 |  | Check events registered to Visitor (Exception) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.049.01 | Attempt to check if Visitor Registered for the event(Visitor object is NULL | FERS.UT.AP491.S.018 | FERS_UT_AP491_S_018.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.049.02 | Attempt to check if Visitor Registered for the event (A general exception occurs) | FERS.UT.AP491.S.018 | FERS_UT_AP491_S_018.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
19 |  | EVENTSERVICEIMPL - updateEventDeletions() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
19.1 |  | Update (Increase) Ticket Inventory (Positive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.050.01 | Update (Increase) Ticket Inventory (valid Event ID) | FERS.UT.AP491.S.019 | FERS_UT_AP491_S_019.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
19.2 |  | Update (Increase) Ticket Inventory (Exception) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.051.01 | Update (Increase) Ticket Inventory (ClassNotFoundException exception occurs) | FERS.UT.AP491.S.019 | FERS_UT_AP491_S_019.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.051.02 | Update (Increase) Ticket Inventory (SQLException exception occurs) | FERS.UT.AP491.S.019 | FERS_UT_AP491_S_019.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.051.03 | Update (Increase) Ticket Inventory (Exception exception occurs) | FERS.UT.AP491.S.019 | FERS_UT_AP491_S_019.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
20 |  | VISITORSERVICEIMPL - createVisitor() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
20.1 |  | Create Visitor (Positive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.052.01 | Attempt to create a new visitor (visitor account created) | FERS.UT.AP491.S.020 | FERS_UT_AP491_S_020.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
20.2 |  | Create Visitor (Negative) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.053.01 | Attempt to create a new visitor (visitor account NOT created) | FERS.UT.AP491.S.020 | FERS_UT_AP491_S_020.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
20.3 |  | Create Visitor (Exception) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.054.01 | Attempt to create a new visitor (No visitor object) | FERS.UT.AP491.S.020 | FERS_UT_AP491_S_020.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.054.02 | Attempt to create a new visitor (ClassNotFoundException exception occurs) | FERS.UT.AP491.S.020 | FERS_UT_AP491_S_020.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.054.03 | Attempt to create a new visitor (SQLException exception occurs) | FERS.UT.AP491.S.020 | FERS_UT_AP491_S_020.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
21 |  | VISITORSERVICEIMPL - searchVisitor() | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
21.1 |  | Search Visitor (Positive) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.055.01 | Attempt to Find Visitor in Database (username/password combo is valid) | FERS.UT.AP491.S.021 | FERS_UT_AP491_S_021.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
21.2 |  | Search Visitor (Negative) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.056.01 | Attempt to Find Visitor in Database (username/password combo is not valid) | FERS.UT.AP491.S.021 | FERS_UT_AP491_S_021.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
21.3 |  | Search Visitor (Exception) | [65 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.057.01 | Attempt to Find Visitor in Database (ClassNotFoundException exception occurs) | FERS.UT.AP491.S.021 | FERS_UT_AP491_S_021.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.057.02 | Attempt to Find Visitor in Database (SQLException exception occurs) | FERS.UT.AP491.S.021 | FERS_UT_AP491_S_021.java | [63 empty] | Ganapati Narayn Bhat | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
22 |  | VISITORSERVICEIMPL - RegisterVisitor() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
22.1 |  | Register Visitor to Event (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.058.01 | Attempt to Register Visitor to Event (valid Visitor account, valid Event ID) | FERS.UT.AP491.S.022 | FERS_UT_AP491_S_022.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
22.2 |  | Register Visitor to Event (Negative) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.059.01 | Attempt to Register Visitor to Event (invalid Visitor account) | FERS.UT.AP491.S.022 | FERS_UT_AP491_S_022.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
22.3 |  | Register Visitor to Event (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.060.01 | Attempt to Register Visitor to Event (ClassNotFoundException exception occurred) | FERS.UT.AP491.S.022 | FERS_UT_AP491_S_022.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.060.02 | Attempt to Register Visitor to Event (SQL Exception exception occurred) | FERS.UT.AP491.S.022 | FERS_UT_AP491_S_022.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
23 |  | VISITORSERVICEIMPL - showRegisteredEvents() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
23.1 |  | Show Events Visitor Registered For (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.061.01 | Attempt to Show Events Visitor Registered For (valid Visitor account) | FERS.UT.AP491.S.023 | FERS_UT_AP491_S_023.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
23.2 |  | Show Events Visitor Registered For (Negative) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.062.01 | Attempt to Show Events Visitor Registered For (invalid Visitor account) | FERS.UT.AP491.S.023 | FERS_UT_AP491_S_023.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
23.3 |  | Show Events Visitor Registered For (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.063.01 | Attempt to Show Events Visitor Registered For (ClassNotFoundException exception occurred) | FERS.UT.AP491.S.023 | FERS_UT_AP491_S_023.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.063.02 | Attempt to Show Events Visitor Registered For (SQL Exception exception occurred) | FERS.UT.AP491.S.023 | FERS_UT_AP491_S_023.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
24 |  | VISITORSERVICEIMPL - updateVisitorDetails() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
24.1 |  | Update Visitor Information (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.064.01 | Attempt to Update Visitor Information (Visitor exists in system) | FERS.UT.AP491.S.024 | FERS_UT_AP491_S_024.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
24.2 |  | Update Visitor Information (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.065.01 | Attempt to Update Visitor Information (ClassNotFoundException exception occurred) | FERS.UT.AP491.S.024 | FERS_UT_AP491_S_024.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.065.02 | Attempt to Update Visitor Information (SQLException exception occurred) | FERS.UT.AP491.S.024 | FERS_UT_AP491_S_024.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
25 |  | VISITORSERVICEIMPL - unregisterEvent() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
25.1 |  | Unregister the visitor from an event (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.066.01 | Attempt to unregister visitor from an event (valid visitor object and event ID) | FERS.UT.AP491.S.025 | FERS_UT_AP491_S_025.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
25.2 |  | Unregister the visitor from an event (Negative) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.067.01 | Attempt to unregister visitor from an event (invalid eventID) | FERS.UT.AP491.S.025 | FERS_UT_AP491_S_025.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
25.3 |  | Unregister the visitor from an event (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.068.01 | Attempt to unregister visitor from an event (statement object not available) | FERS.UT.AP491.S.025 | FERS_UT_AP491_S_025.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.068.02 | Attempt to unregister visitor from an event (connection object not available) | FERS.UT.AP491.S.025 | FERS_UT_AP491_S_025.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
26 |  | FERSGENERICEXCEPTION - FERSGenericException() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
26.1 |  | Create an Exception (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.069.01 | Attempt to throw an Exception (with a message and throwable object) | FERS.UT.AP491.S.026 | FERS_UT_AP491_S_026.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
26.2 |  | Create an Exception (Negative) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.070.01 | Attempt to throw an Exception (NULL message and throwable object) | FERS.UT.AP491.S.026 | FERS_UT_AP491_S_026.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
26.3 |  | Create an Exception (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.071.01 | Attempt to throw an Exception (with a message and non-throwable object) | FERS.UT.AP491.S.026 | FERS_UT_AP491_S_026.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
27 |  | FERSDATACONNECTION - createConnection() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
27.1 |  | Create a Connection (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.072.01 | Attempt to create a connection(all parameters are correct) | FERS.UT.AP491.S.027 | FERS_UT_AP491_S_027.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
27.2 |  | Create a Connection (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.073.01 | Attempt to create a connection(JDBC Driver not found) | FERS.UT.AP491.S.027 | FERS_UT_AP491_S_027.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.073.02 | Attempt to create a connection(Unable to get a connection) | FERS.UT.AP491.S.027 | FERS_UT_AP491_S_027.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
28 |  | FERSDATACONNECTION - closeConnection() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
28.1 |  | Close Connection (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.074.01 | Attempt to close a connection (all objects are valid) | FERS.UT.AP491.S.028 | FERS_UT_AP491_S_028.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
28.2 |  | Close Connection (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.075.01 | Attempt to close a connection (statement object not available) | FERS.UT.AP491.S.028 | FERS_UT_AP491_S_028.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
29 |  | VISITORCONTROLLER - searchEventsByName() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
29.1 |  | Search Events - Positive | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.076.01 | Attempt to search for an event session by name on the Festival Portal Page (valid visitor and event name) - multiple events returned | FERS.UT.AP491.S.029 | FERS_UT_AP491_S_029.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.076.02 | Attempt to search for an event session by name on the Festival Portal Page (valid visitor and valid eventname) - one event session returned | FERS.UT.AP491.S.029 | FERS_UT_AP491_S_029.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
29.2 |  | Search Events - Negative | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.077.01 | Attempt to search for an event session by name on the Festival Portal Page (valid visitor and invalid eventname) - no event sessions returned | FERS.UT.AP491.S.029 | FERS_UT_AP491_S_029.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
29.3 |  | Search Events - Exception | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.078.01 | Attempt to search for an event session by name on the Festival Portal Page (missing Visitor attribute) | FERS.UT.AP491.S.030 | FERS_UT_AP491_S_030.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.078.02 | Attempt to search for an event session by name on the Festival Portal Page (missing request object) | FERS.UT.AP491.S.030 | FERS_UT_AP491_S_030.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.078.03 | Attempt to search for an event session by name on the Festival Portal Page (missing response object) | FERS.UT.AP491.S.030 | FERS_UT_AP491_S_030.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
30 |  | VISITORCONTROLLER - searchEventsByNameCatalog() | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
30.1 |  | Search Events by Name in Event Catalog (Positive) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.079.01 | Attempt to search for an event session by name on the Event Catalog Page (valid visitor and event name) - multiple events returned | FERS.UT.AP491.S.031 | FERS_UT_AP491_S_031.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.079.02 | Attempt to search for an event session by name on the Event Catalog Page (valid visitor and invalid eventname) - one event session returned | FERS.UT.AP491.S.031 | FERS_UT_AP491_S_031.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
30.2 |  | Search Events by Name in Event Catalog (Negative) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.080.01 | Attempt to search for an event session by name on the Event Catalog Page (valid visitor and invalid eventname) - no event sessions returned | FERS.UT.AP491.S.031 | FERS_UT_AP491_S_031.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
30.3 |  | Search Events by Name in Event Catalog (Exception) | [65 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.081.01 | Attempt to search for an event session by name on the Event Catalog Page (missing Visitor attribute) | FERS.UT.AP491.S.032 | FERS_UT_AP491_S_032.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.081.02 | Attempt to search for an event session by name on the Event Catalog Page (missing request object) | FERS.UT.AP491.S.032 | FERS_UT_AP491_S_032.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.081.03 | Attempt to search for an event session by name on the Event Catalog Page (missing response object) | FERS.UT.AP491.S.032 | FERS_UT_AP491_S_032.java | [63 empty] | Amlan Mahapatra | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
31 |  | VISITORCONTROLLER - showEventsAsc() | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
31.1 |  | Show Events in Ascending Order (Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.082.01 | Sort event sessions by name in ascending order on the Festival Portal Page (valid visitor and event name) - multiple events returned | FERS.UT.AP491.S.033 | FERS_UT_AP491_S_033.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.082.02 | Sort event sessions by name in ascending order on the Festival Portal Page (valid visitor and invalid eventname) - one event session returned | FERS.UT.AP491.S.033 | FERS_UT_AP491_S_033.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
31.2 |  | Show Events in Ascending Order (Negative) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.083.01 | Sort event sessions by name in ascending order on the Festival Portal Page (valid visitor and invalid eventname) - no event sessions returned | FERS.UT.AP491.S.033 | FERS_UT_AP491_S_033.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
31.3 |  | Show Events in Ascending Order (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.084.01 | Sort event sessions by name in ascending order on the Festival Portal Page (missing Visitor attribute) | FERS.UT.AP491.S.034 | FERS_UT_AP491_S_034.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.084.02 | Sort event sessions by name in ascending order on the Festival Portal Page (missing request object) | FERS.UT.AP491.S.034 | FERS_UT_AP491_S_034.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.084.03 | Sort event sessions by name in ascending order on the Festival Portal Page (missing response object) | FERS.UT.AP491.S.034 | FERS_UT_AP491_S_034.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
32 |  | VISITORCONTROLLER - showEventsDesc() | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
32.1 |  | Show Events in Descending Order (Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.085.01 | Sort event sessions by name in descending order on the Festival Portal Page (valid visitor and event name) - multiple events returned | FERS.UT.AP491.S.035 | FERS_UT_AP491_S_035.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.085.02 | Sort event sessions by name in descending order on the Festival Portal Page (valid visitor and invalid eventname) - one event session returned | FERS.UT.AP491.S.035 | FERS_UT_AP491_S_035.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
32.2 |  | Show Events in Descending Order (Negative) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.086.01 | Sort event sessions by name in descending order on the Festival Portal Page (valid visitor and invalid eventname) - no event sessions returned | FERS.UT.AP491.S.035 | FERS_UT_AP491_S_035.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
32.3 |  | Show Events in Descending Order (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.087.01 | Sort event sessions by name in descending order on the Festival Portal Page (missing Visitor attribute) | FERS.UT.AP491.S.036 | FERS_UT_AP491_S_036.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.087.02 | Sort event sessions by name in descending order on the Festival Portal Page (missing request object) | FERS.UT.AP491.S.036 | FERS_UT_AP491_S_036.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.087.03 | Sort event sessions by name in descending order on the Festival Portal Page (missing response object) | FERS.UT.AP491.S.036 | FERS_UT_AP491_S_036.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
33 |  | VISITORCONTROLLER - showEventsCatalogAsc() | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
33.1 |  | Show Events in Ascending Order in Event Catalog (Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.088.01 | Sort event sessions by name in ascending order on the Event Catalog Page (valid visitor and event name) - multiple events returned | FERS.UT.AP491.S.037 | FERS_UT_AP491_S_037.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.088.02 | Sort event sessions by name in ascending order on the Event Catalog Page (valid visitor and invalid eventname) - one event session returned | FERS.UT.AP491.S.037 | FERS_UT_AP491_S_037.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
33.2 |  | Show Events in Ascending Order in Event Catalog (Negative) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.089.01 | Sort event sessions by name in ascending order on the Event Catalog Page (valid visitor and invalid eventname) - no event sessions returned | FERS.UT.AP491.S.037 | FERS_UT_AP491_S_037.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
33.3 |  | Show Events in Ascending Order in Event Catalog (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.090.01 | Sort event sessions by name in ascending order on the Event Catalog Page (missing Visitor attribute) | FERS.UT.AP491.S.038 | FERS_UT_AP491_S_038.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.090.02 | Sort event sessions by name in ascending order on the Event Catalog Page (missing request object) | FERS.UT.AP491.S.038 | FERS_UT_AP491_S_038.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.090.03 | Sort event sessions by name in ascending order on the Event Catalog Page (missing response object) | FERS.UT.AP491.S.038 | FERS_UT_AP491_S_038.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
34 |  | VISITORCONTROLLER - showEventsCatalogDesc() | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
34.1 |  | Show Events in Descending Order in Event Catalog (Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.091.01 | Sort event sessions by name in descending order on the Event Catalog Page (valid visitor and event name) - multiple events returned | FERS.UT.AP491.S.039 | FERS_UT_AP491_S_039.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.091.02 | Sort event sessions by name in descending order on the Event Catalog Page (valid visitor and invalid eventname) - one event session returned | FERS.UT.AP491.S.039 | FERS_UT_AP491_S_039.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
34.2 |  | Show Events in Descending Order in Event Catalog (Negative) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.092.01 | Sort event sessions by name in descending order on the Event Catalog Page (valid visitor and invalid eventname) - no event sessions returned | FERS.UT.AP491.S.039 | FERS_UT_AP491_S_039.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
34.3 |  | Show Events in Descending Order in Event Catalog (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.093.01 | Sort event sessions by name in descending order on the Event Catalog Page (missing Visitor attribute) | FERS.UT.AP491.S.040 | FERS_UT_AP491_S_040.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.093.02 | Sort event sessions by name in descending order on the Event Catalog Page (missing request object) | FERS.UT.AP491.S.040 | FERS_UT_AP491_S_040.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.093.03 | Sort event sessions by name in descending order on the Event Catalog Page (missing response object) | FERS.UT.AP491.S.040 | FERS_UT_AP491_S_040.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
35 |  | EVENTSERVICEIMPL -getAllEvents(String) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
35.1 |  | Get all available events by Name (Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.094.01 | Attempt to retrieve information on all upcoming events whose name contains a specified text (Events found) | FERS.UT.AP491.S.041 | FERS_UT_AP491_S_041.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
35.2 |  | Get all available events by Name (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.095.01 | Attempt to retrieve information on all upcoming events whose name contains a specified text(ClassNotFoundException exception occurs) | FERS.UT.AP491.S.042 | FERS_UT_AP491_S_042.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.095.02 | Attempt to retrieve information on all upcoming events whose name contains a specified text(SQLException exception occurs) | FERS.UT.AP491.S.042 | FERS_UT_AP491_S_042.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
36 |  | EVENTSERVICEIMPL -getAllEventsAsc() | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
36.1 |  | Get all available events in Ascending Order (Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.096.01 | Attempt to retrieve information on all upcoming events in ascending order (Events found) | FERS.UT.AP491.S.043 | FERS_UT_AP491_S_043.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
36.2 |  | Get all available events in Ascending Order (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.097.01 | Attempt to retrieve information on all upcoming events in ascending order (ClassNotFoundException exception occurs) | FERS.UT.AP491.S.044 | FERS_UT_AP491_S_044.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.097.02 | Attempt to retrieve information on all upcoming events in ascending order (SQLException exception occurs) | FERS.UT.AP491.S.044 | FERS_UT_AP491_S_044.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
37 |  | EVENTSERVICEIMPL -getAllEventsDesc() | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
37.1 |  | Get all available events in Descending Order(Positive) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.098.01 | Attempt to retrieve information on all upcoming events in descending order (Events found) | FERS.UT.AP491.S.045 | FERS_UT_AP491_S_045.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
37.2 |  | Get all available events in Descending Order (Exception) | [65 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27
| FERS.UT.AP491.TS.099.01 | Attempt to retrieve information on all upcoming events in descending order(ClassNotFoundException exception occurs) | FERS.UT.AP491.S.046 | FERS_UT_AP491_S_046.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
| FERS.UT.AP491.TS.099.02 | Attempt to retrieve information on all upcoming events in descending order (SQLException exception occurs) | FERS.UT.AP491.S.046 | FERS_UT_AP491_S_046.java | [63 empty] | Ahammad Basha Kurnool | Completed | Not Started | Not Started | 2015-05-27 | 2015-05-27 | bar: 2015-05-27
END OF TEST CYCLE CONTROL SHEET